## WASH Projects
Intervention | 2019-05-31 | 2019-06-30 | 2019-07-30 | 2019-08-29 | 2019-09-28 | 2019-10-28 | 2019-11-27 | 2019-12-27 | 2020-01-20 | 2020-02-20 | 2020-03-20 | 2020-04-20 | 2020-05-20 | 2020-06-20 | 2020-07-20 | 2020-08-20 | Sept-20 | 2020-10-20 | 2020-11-20 | 2020-12-21 | 2021-01-21 | 2021-02-21 | 2021-03-21 | 2021-04-21 | Totals | Est.Totals
New
Bathroom | 8 | 2 | 10 | 3 | 4 |  |  |  | 22 | 1 | 8 | 2 | 11 | 12 |  |  |  |  | 1 | 17 |  |  |  |  | 101
Cement Floor | 2019-09-28: 1; 2019-10-28: 2; 2019-11-27: 41; 2020-01-20: 13; 2020-03-20: 9 |  |  |  | 1 |  |  |  |  | 67
Water Filter |  | 24 | 19 | 18 | 4 | 28 | 16 | 42 | 15 |  | 15 |  | 38 | 6 | 2 |  |  | 20 |  | 18 | 8 | 16 | 22 |  | 311
Rainwater Collection | 2019-07-30: 1; 2019-08-29: 2 | [8 empty] | 3
Hand-washing stations | 2020-03-20: 20; 2020-05-20: 31; 2020-06-20: 100 |  |  | 2 | 25 | 10 | 5 | 5 |  | 198
Water Access Projects | [24 empty] | 0
Total New | 8 | 26 | 30 | 23 | 9 | 30 | 57 | 42 | 50 | 1 | 52 | 2 | 80 | 118 | [10 empty] | 680
Cumulative
Bathroom | 8 | 10 | 20 | 23 | 27 | 27 | 27 | 27 | 49 | 50 | 58 | 60 | 71 | 83 | 83 | 83 | 83 | 83 | 84 | 101 | 101 | 101 | 101 |  | 101
Water Filter | 0 | 24 | 43 | 61 | 65 | 93 | 109 | 151 | 166 | 166 | 181 | 181 | 219 | 225 | 227 | 227 | 227 | 247 | 247 | 265 | 273 | 289 | 311 |  | 67
Rainwater Collection | 0 | 0 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 311
Cement Floor | 0 | 0 | 0 | 0 | 1 | 3 | 44 | 44 | 57 | 57 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 67 | 67 | 67 | 67 |  | 3
Hand-washing stations | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 51 | 151 | 151 | 151 | 151 | 151 | 153 | 178 | 188 | 193 | 198 |  | 198
Water Access Projects | [24 empty] | 0
Total Cumulative | 8 | 34 | 64 | 87 | 96 | 126 | 183 | 225 | 275 | 276 | 328 | 330 | 410 | 528 | 530 | 530 | 530 | 550 | 553 | 614 |  |  |  |  | 680
Note on B3: ====== ID#AAAAKAdRrs8 scott coppa (2020-07-22 23:41:31) +carly.pablos@puente-dr.com

## Project Breakdown by Community
Los Gajitos
Bathrooms | Floors | Water Filters | Rainwater Collection | Handwashing Stations | community_focus = [
27 | 44 | 74 | 2 |  | "Los Gajitos",
"El Canal",
Canada Las Palmas |  |  |  |  | "Cañada las Palmas",
Bathrooms | Floors | Water Filters | Rainwater Collection | Handwashing Stations | "El Convento",
16 | 13 | 9 | 0 |  | "Los Embassadores",
"Los Mangos",
"Cuidad de Dios",
]
El Canal
Bathrooms | Floors | Water Filters | Rainwater Collection | Handwashing Stations
33 | 11 | 17 | 0
La Luisa
Bathrooms | Floors | Water Filters | Rainwater Collection | Handwashing Stations
6 | 0 | 1 | 0
San Isidro
Bathrooms | Floors | Water Filters | Rainwater Collection | Handwashing Stations
2 | 0 | 0 | 0
Los Embassadores
Bathrooms | Floors | Water Filters | Rainwater Collection | Handwashing Stations
6 | 0 | 31 | 0
Barrio El Padre
Bathrooms | Floors | Water Filters | Rainwater Collection | Handwashing Stations
0 | 0 | 16 | 0
Barrio Juan Pedro
Bathrooms | Floors | Water Filters | Rainwater Collection | Handwashing Stations
0 | 0 | 1 | 0
Barrio San Juan
Bathrooms | Floors | Water Filters | Rainwater Collection | Handwashing Stations
0 | 0 | 1 | 0
El Cercado
Bathrooms | Floors | Water Filters | Rainwater Collection | Handwashing Stations
0 | 0 | 16 | 0
El Arenazo
Bathrooms | Floors | Water Filters | Rainwater Collection | Handwashing Stations
0 | 0 | 7 | 0
Colonial Japonesa
Bathrooms | Floors | Water Filters | Rainwater Collection | Handwashing Stations
0 | 0 | 10 | 0
Calle Sanchez
Bathrooms | Floors | Water Filters | Rainwater Collection | Handwashing Stations
0 | 0 | 2 | 0
El Gajo
Bathrooms | Floors | Water Filters | Rainwater Collection | Handwashing Stations
0 | 0 | 1 | 0
El Paraiso
Bathrooms | Floors | Water Filters | Rainwater Collection | Handwashing Stations
0 | 0 | 6 | 0
El Tornado
Bathrooms | Floors | Water Filters | Rainwater Collection | Handwashing Stations
0 | 0 | 3 | 0
La Altagracia
Bathrooms | Floors | Water Filters | Rainwater Collection | Handwashing Stations
0 | 0 | 11 | 0
La Cotorra
Bathrooms | Floors | Water Filters | Rainwater Collection | Handwashing Stations
0 | 0 | 14
El Valle
Bathrooms | Floors | Water Filters | Rainwater Collection | Handwashing Stations
0 | 0 | 1 | 0
Barrio Las Flores
Bathrooms | Floors | Water Filters | Rainwater Collection | Handwashing Stations
0 | 0 | 1 | 0 | 0
La Sabina
Bathrooms | Floors | Water Filters | Rainwater Collection | Handwashing Stations
0 | 0 | 1 | 0
La Planta
Bathrooms | Floors | Water Filters | Rainwater Collection | Handwashing Stations
0 | 0 | 1 | 0
Las Mercedes
Bathrooms | Floors | Water Filters | Rainwater Collection | Handwashing Stations
0 | 0 | 3 | 0
Los Pinos
Bathrooms | Floors | Water Filters | Rainwater Collection | Handwashing Stations
0 | 0 | 1 | 0
Pueblo Nuevo
Bathrooms | Floors | Water Filters | Rainwater Collection | Handwashing Stations
0 | 0 | 2 | 0
Paragua
Bathrooms | Floors | Water Filters | Rainwater Collection | Handwashing Stations
0 | 0 | 1 | 0 | 0
Santa Rosa
Bathrooms | Floors | Water Filters | Rainwater Collection | Handwashing Stations
0 | 0 | 10 | 1 | 0
Villa Hortaliza
Bathrooms | Floors | Water Filters | Rainwater Collection | Handwashing Stations
0 | 0 | 11 | 0 | 0
Villa Montana
Bathrooms | Floors | Water Filters | Rainwater Collection | Handwashing Stations
0 | 0 | 16 | 0 | 0
Villa Pinales
Bathrooms | Floors | Water Filters | Rainwater Collection | Handwashing Stations
0 | 0 | 2 | 0 | 0

## COVID Response
Intervention | 2020-03-20 | 2020-04-19 | 2020-05-19 | 2020-06-18 | 2020-07-18 | 2020-08-17 | Totals | Est.Totals
New
Homemade masks | 2020-04-19: 400 | 400
n95 masks | 2020-03-20: 15; 2020-04-19: 85; 2020-07-18: 245 | 100
Medical masks | 2020-03-20: 120 | 120
Gloves | 2020-03-20: 100; 2020-04-19: 200; 2020-07-18: 1250 | 300
Hazmat Suits | 2020-03-20: 60; 2020-07-18: 40 | 60
Visors | 2020-03-20: 15; 2020-07-18: 20 | 15
Protective glasses | 2020-04-19: 50 | 50
Handwashing stations | 2020-03-20: 20 | 20
Total New | 2020-03-20: 295; 2020-04-19: 685 | 980
Cumulative
Homemade masks | 0 | 400 | 400 | 400 | 400 | 400 | 400
n95 masks | 15 | 100 | 100 | 100 | 345 | 345 | 100
Medical Masks | 120 | 120 | 120 | 120 | 120 | 120 | 120
Gloves | 100 | 300 | 300 | 300 | 1550 | 1550 | 300
Hazmat Suits | 60 | 60 | 60 | 60 | 100 | 100 | 60
Visors | 15 | 15 | 15 | 15 | 35 | 35 | 15
Glasses | 0 | 50 | 50 | 50 | 50 | 50 | 50
Handwashing stations | 20 | 20 | 20 | 20 | 20 | 20 | 20
Total Cumulative | 295 | 980 | 980 | 980 | 2515 | 2515 | 980

## MapCommunities
Community | Bathrooms | Floors | Water Filters | Rainwater Collection | Handwashing Stations
Los Gajitos | 27 | 44 | 74 | 2 | 0
El Canal | 33 | 11 | 17 | 0 | 0
Cañada las Palmas | 16 | 13 | 9 | 0 | 0
Los Embassadores | 6 | 0 | 31 | 0 | 0